## Team
Initials | First | Last | Email | GitHub Username
hc | Himabindu | Chaturvedula | hchaturv@stevens.edu | binduchaturvedula
sg | Stanislav | Grozny | sgrozny@stevens.edu | sgrozny
lg | Le | Zhanz | lzhang40@stevens.edu | zhangle2015
|  |  | GitHub Repository: | CS555_GEDCOM

## Backlog
Sprint | Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed | Added
1 | US01 | Death before birth |  | lz | done | 25 | 30 | 25 | 20 | 2015-03-03
1 | US02 | Gender on parent is wrong |  | lz | done | 20 | 25 | 20 | 20 | 2015-03-03
1 | US03 | Missing birth date |  | hc | Done | 25 | 30 | 25 | 30 | 2015-03-03
1 | US04 | More than 15 kids |  | sg | Done | 20 | 20 | 22 | 30 | 2015-03-03
1 | US05 | Two Identical Indviduals |  | sg | Done | 15 | 15 | 22 | 20 | 2015-03-03
2 | US06 | nothing can happen after death date |  | lz | done | 25 | 20 | 25 | 20 | 2015-03-24
2 | US07 | divorce date cant be before married date |  | lz | done | 30 | 30 | 30 | 30 | 2015-03-24
2 | US08 | Loop exists |  | sg | done | 50 | 60 | 130 | 120 | 2015-03-17
2 | US09 | Individual is both a spouse and a child |  | sg | done | 15 | 12 | 20 | 10 | 2015-03-23
3 | US10 | Individual records should match family recored |  | sg | done | 50 | 60 | 90 | 90 | 2015-04-07
2 | US11 | Two Identical Children in a family |  | hc | done | 15 | 30 | 15 | 50 | 2015-03-24
2 | US12 | No marriage date in a family |  | hc | done | 15 | 30 | 25 | 60 | 2015-03-24
3 | US13 | Moms give birth |  | hc | Done | 25 | 100 | 38 | 80 | 2015-04-07
3 | US14 | Parents are older |  | hc | Done | 30 | 20 | 38 | 20 | 2015-04-07
4 | US15 | Be Alive First |  | hc |  | 50 | 40
4 | US16 | Not always 9 months |  | hc |  | 100 | 120
4 | US17 | Dual Marriage
3 | US18 | Mom is under 5 years old |  | lz | In Progress | 25 | 30 | 30 | 40
4 | US19 | Sibling Incest |  | lz |  | 100 | 120
| US20 | Dual Role |  | lz
| US21 | Polygamy
3 | US22 | Age is over 130 |  | lz | In Progress | 25 | 30 | 30 | 40
| US23 | Only 1 set of parents or is it
4 | US24 | We aren't seahorses |  | sg |  | 50 | 30
4 | US25 | NJ Pre 2013 |  | sg |  | 60 | 60
| US26 | Third is more legal
| US27 | Teddy's Home
3 | US28 | Family Records should match individaul records |  | sg | done | 150 | 60 | 200 | 90 | 2015-04-07

## Stories
Story ID | Story Name | Story Description | Acc Tests | Est Size | Est Time
US01 | Gender on parent | Make sure the gender on parent is correct | AT01 | 40 | 45
US02 | Death before marriage | Make sure the Marriage date is before death | AT02 | 30 | 25
US03 | Missing birth date | Make sure each and every individual with birth date | AT03 | 30 | 30
US04 | More than 15 kids | Make sure a family contains less than 15 kids | AT04 | 20 | 20
US05 | Two Identical Indvidauls | Make sure two people with the same name and birthdate don't appear | AT05 | 20 | 15
US06 | about death problem | nothing can happen after death date | AT06 | 30 | 40
US07 | about divorce date problem | divorce date cant be before married date | AT07 | 40 | 45
US08 | Loop exists | An individual is an ancestral child of self, | AT08 | 50 | 60
US09 | Individual is both a spouse and a parent | Check to see that an individual isn’t both a spouse and a child | AT09 | 15 | 12
US10 | Individual records don't match family recored | Make sure all info for individuals matches family records | AT10 | 50 | 60
US11 | Two Identical Children in a family | Two children can't share a name and birthdate
US12 | No marriage date in a family | Marriage date in a family doesn't exist
US13 | Moms give birth | BirthDate of children can't be after deathdate of mother
US14 | Parents are older | Birthdate of children can't be before birthdate of parents
US15 | Be Alive First | Deathdate of indvidual can't be before birthdate
US16 | Not always 9 months | Birthdate of Childrenin reasonable parameters with same mother , 90 -145 days are the apprixamte records for longest twin gap and earliest birth
US17 | Dual Marriage | Error if: Two marraiage events without a divorce or death occurance
US18 | Mom is under 5 years old | Mom is under 5 years old (record)
US19 | Sibling Incest | Siblings can't be married if biological siblings
US20 | Dual Role | Indvidual can't be both a spouse and a child to same family
US21 | Polygamy | Individual is a spouse to multipile families without a Divore or Deathdate
US22 | Age is over 130 | Age is over 130
US23 | Only 1 set of parents or is it | An individual can't be a child to two families, unless a remarriage occured
US24 | We aren't seahorses | Only husband but no wife
US25 | NJ Pre 2013 | A family can't have more than 1 of each spouses
US26 | Third is more legal | first cousins should not marry one another
US27 | Teddy's Home | aunts and uncles should not marry their nephews or nieces
US28 | Family Records should match individaul records | Family Records should match individaul records

## Tests
AT ID | Story ID | Story Name | Input | Expected Output | Status
AT 01 | US01 | Death before birth | GED file, Individual Id,Bdays,Ddays | judge whether death before birth | done
AT 02 | US02
AT 03 | US03 | Missing birthdate | GED file, Individual Id,Bdays | All individuals with birthdates | Done
AT 04 | US04 | More than 15 Kids | GED File, Fam ID @F6@ has 16 kids. | Only Fam ID @F6@ is alerted and lists all childrens names | Done/Worked/Passed
AT 05 | US05 | Two Idenitcal Indviduals | Copied the information from indvidual 2 and 12 into indvidual 16 and 17 | Alerts to each set of copied indviduals and prints their information | Done/Worked/Passed
AT 06 | US06
AT 07 | US07
AT 08 | US08 | Loop exists | GED File, Where an individaul is a child of its children | Alert if any node(individual) is revisited. So Individual A is looped, so it will alert on A, B, and D because B and D's children are A | Done
AT 09 | US09 | Individual is both a spouse and a parent | GED File, FAMS and FAMC match on an indvidual | Individual @SG-2-3-BCP@ will be spotted | Done
AT 10 | US10 | Individual records don't match family record | GED File, a FAMS or FAMC call to a family where that family doesn't have a matching tag | Individuals that have records that don't match to proper family. Will include: Individual record exists but family equivalent is null, Individual record exists but family record doesn't match, individual record exists but family to which it points doesn't | Done
AT 11 | US11 | Missing Marriage date for Family | GED file, family structure and total number of families | All families should have maggiage date | Done
AT 12 | US12 | checking for Same name and birth date for family | GED file, Family and Individual Structures | No children in family should have sama name and birth date | Done
AT 13 | US13 | mom gives birth | GED file, family structure and individual structure. | Mom with death date before birth date of kid@HC-3-1-F1@ | Done/Worked/Passed
AT 14 | US14 | Parents are older | GED file, family structure and individual structure. | Mom with birth date later birth date of kid@HC-3-1-F3@ | Done/Worked/Passed
AT18 | US18 | Mom is under 5 years old | GEDCOM file checks every wifes birtday vs all of her kids if the agedifference is 5 years or less it’s a problem | Return all mothers whose age was 5 or less at birthtime(regardless of current age) | In progress
AT22 | US22 | Age is over 130 | GED file, family structure and individual structure. | All individuals who are over 130 from todays date | In progress
AT 28 | US28 | Family Records should match individaul records | GED file, Family and Individual Structures | Families that have records that don't match to proper individual records. Will include: WIFE or HUSB tags point to individuals whose Spouse tag doesn't match family id, or Spouse tag is null, or individual doesn't exsist | Done

## Burndown
Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
2015-02-17 | 28 |  | 0
2015-03-03 | 24 | 4 | 53 | 60 | 53
2015-03-24 | 20 | 4 | 215 | 365 | 26.6301
2015-04-07 | 13 | 7 | 433 | 300 | 43.6
2015-04-21 |  | 13 | 30 | 40 | -604.5
2015-05-05 |  | 0 | 0 | 0 | #DIV/0!

## Sprint1
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US01 | Death before birth | AT01, AT02 | hm | Done | 150 | 60 | 120 | 90 | 2014-09-24
US02 | Death before birth | AT03 | LZ | DONE | 100 | 60 | 70 | 70
US03 | gender is wrong | AT04 | LZ | DONE | 100 | 60 | 60 | 30
US04 | More Than 15 Kids | AT04 | sg | Done | 20 | 20 | 22 | 30 | 40604
US05 | Two Identical Indvidauls | AT05 | sg | Done | 20 | 15 | 22 | 20
Review Results
Keep doing:
Meet twice a week
Text everyone when you discover a problem
Avoid:
Forgetting to commit changes to GitHub

## Sprint2
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US06 | nothing can happen after death date | AT06 | lz | done | 30 | 35 | 35 | 50 | 0.13043
US07 | divorce date cant be before married date | AT07 | lz | done | 30 | 40 | 50 | 75
US08 | Loop exists | AT08 | sg | done | 50 | 60 | 75 | 120
US09 | Individual is both a spouse and a child | AT09 | sg | done | 15 | 12 | 20 | 10
US11 | Missing Marriage date | AT11 | hc | done | 15 | 30 | 15 | 50
US12 | Two identical children in family | AT12 | hc | done | 15 | 40 | 20 | 60

## Sprint3
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US10 | Individual records should match family recored | AT10 | sg | done | 50 | 60 | 90 | 90 | 2015-04-07
US28 | Family Records should match individaul records | AT28 | sg | done | 150 | 60 | 200 | 90 | 2015-04-07
US13 | Mom gives birth | AT 13 | hc | done | 30 | 100 | 43 | 120 | 2015-04-07
US14 | parents are older | AT 14 | hc | done | 60 | 20 | 40 | 10 | 2015-04-07
US18 | Mom is under 5 years old | AT 18 | lz | In progress | 25 | 30 | 30 | 40
US22 | Age is over 130 | AT 22 | lz | In progress | 25 | 30 | 30 | 40
Review Results
Most productive sprint
Keep doing:
Meet twice a week
Set weekly deadlines
Avoid:
Not communicating more whena problem appears

## Sprint4
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed | Comment
US24 | We aren't seahorses | AT24 | lz | done | 50 | 30
US25 | NJ Pre 2013 | AT25 | sg |  | 60 | 60 |  |  |  | Will probably take much longer as arcitecture will have to be modified
US16 | Not always 9 months | AT16 | hc |  | 100 | 120
US19 | Sibling Incest | AT19 | sg |  | 100 | 120
US15 | Be Alive First | AT15 | hc |  | 50 | 40
US20 | partents are older than 18 | AT18 | lz | done | 25 | 30 | 30 | 40
US
Review Results
Keep doing:
Avoid:

## Sprint5
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed