## Team
Initials | First | Last | Email | GitHub Username
hc | Himabindu | Chaturvedula | hchaturv@stevens.edu | binduchaturvedula
sg | Stanislav | Grozny | sgrozny@stevens.edu | sgrozny
lg | Le | Zhanz | lzhang40@stevens.edu | zhangle2015
|  |  | GitHub Repository: | CS555_GEDCOM

## Backlog
Sprint | Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed | Added
1 | US01 | Death before birth |  | lz | done | 25 | 30 | 25 | 20 | 2015-03-03
1 | US02 | Gender on parent is wrong |  | lz | done | 20 | 25 | 20 | 20 | 2015-03-03
1 | US03 | Missing birth date |  | hc | Done | 25 | 30 | 25 | 30 | 2015-03-03
1 | US04 | More than 15 kids |  | sg | Done | 20 | 20 | 22 | 30 | 2015-03-03
1 | US05 | Two Identical Indviduals |  | sg | Done | 15 | 15 | 22 | 20 | 2015-03-03
2 | US06 | nothing can happen after death date |  | lz | done | 25 | 20 | 25 | 20 | 2015-03-24
2 | US07 | divorce date cant be before married date |  | lz | done | 30 | 30 | 30 | 30 | 2015-03-24
2 | US08 | Loop exists |  | sg | done | 50 | 60 | 75 | 120 | 2015-03-17
2 | US09 | Individual is both a spouse and a parent |  | sg | done | 15 | 12 | 20 | 10 | 2015-03-23
2 | US10 | Individual records don't match family recored |  | sg | In progress | 50 | 60 | 90 | 75 | In progress
| US11 | Two Identical Children in a family |  | hc
| US12 | No marriage date in a family |  | hc
| US13 | Moms give birth
| US14 | Parents are older
| US15 | Be Alive First
| US16 | Not always 9 months
| US17 | Dual Marriage
| US18 | Mom is under 5 years old
| US19 | Sibling Incest
| US20 | Dual Role
| US21 | Polygamy
| US22 | Age is over 130
| US23 | Only 1 set of parents or is it
| US24 | We aren't seahorses
| US25 | NJ Pre 2013
| US26 | Third is more legal
| US27 | Teddy's Home
| US28 | Family Records should match individaul records

## Stories
Story ID | Story Name | Story Description | Acc Tests | Est Size | Est Time
US01 | Gender on parent | Make sure the gender on parent is correct | AT01 | 40 | 45
US02 | Death before marriage | Make sure the Marriage date is before death | AT02 | 30 | 25
US03 | Missing birth date | Make sure each and every individual with birth date | AT03 | 30 | 30
US04 | More than 15 kids | Make sure a family contains less than 15 kids | AT04 | 20 | 20
US05 | Two Identical Indvidauls | Make sure two people with the same name and birthdate don't appear | AT05 | 20 | 15
US06 | about death problem | nothing can happen after death date | AT06 | 30 | 40
US07 | about divorce date problem | divorce date cant be before married date | AT07 | 40 | 45
US08 | Loop exists | An individual is an ancestral child of self, | AT08 | 50 | 60
US09 | Individual is both a spouse and a parent | Check to see that an individual isn’t both a spouse and a child | AT09 | 15 | 12
US10 | Individual records don't match family recored | Make sure all info for individuals matches family records | AT10 | 50 | 60
US11 | Two Identical Children in a family | Two children can't share a name and birthdate
US12 | No marriage date in a family | Marriage date in a family doesn't exist
US13 | Moms give birth | BirthDate of children can't be after deathdate of mother
US14 | Parents are older | Birthdate of children can't be before birthdate of parents
US15 | Be Alive First | Deathdate of indvidual can't be before birthdate
US16 | Not always 9 months | Birthdate of Childrenin reasonable parameters with same mother , 90 -145 days are the apprixamte records for longest twin gap and earliest birth
US17 | Dual Marriage | Error if: Two marraiage events without a divorce or death occurance
US18 | Mom is under 5 years old | Mom is under 5 years old (record)
US19 | Sibling Incest | Siblings can't be married if biological siblings
US20 | Dual Role | Indvidual can't be both a spouse and a child to same family
US21 | Polygamy | Individual is a spouse to multipile families without a Divore or Deathdate
US22 | Age is over 130 | Age is over 130
US23 | Only 1 set of parents or is it | An individual can't be a child to two families, unless a remarriage occred
US24 | We aren't seahorses | Only husband but no wife
US25 | NJ Pre 2013 | A family can't have more than 1 of each spouses
US26 | Third is more legal | first cousins should not marry one another
US27 | Teddy's Home | aunts and uncles should not marry their nephews or nieces
US28 | Family Records should match individaul records | Family Records should match individaul records

## Tests
AT ID | Story ID | Story Name | Input | Expected Output | Status
AT 01 | US01 | Death before birth | GED file, Individual Id,Bdays,Ddays | judge whether death before birth | done
AT 02 | US02
AT 03 | US03 | Missing birthdate | GED file, Individual Id,Bdays | All individuals with birthdates | Done
AT 04 | US04 | More than 15 Kids | GED File, Fam ID @F6@ has 16 kids. | Only Fam ID @F6@ is alerted and lists all childrens names | Done/Worked/Passed
AT 05 | US05 | Two Idenitcal Indviduals | Copied the information from indvidual 2 and 12 into indvidual 16 and 17 | Alerts to each set of copied indviduals and prints their information | Done/Worked/Passed
AT 06 | US06
AT 07 | US07
AT 08 | US08 | Loop exists | GED File, Where an individaul is a child of its children | Alert if any node(individual) is revisited. So Individual A is looped, so it will alert on A, B, and D because B and D's children are A | Done
AT 09 | US09 | Individual is both a spouse and a parent | GED File, FAMS and FAMC match on an indvidual | Individual @SG-2-3-BCP@ will be spotted | Done
AT 10 | US10 | Individual records don't match family recored | GED File, a FAMS or FAMC call to a family where that family doesn't have a matching tag | Individuals @SG-2-3-RDM@ and @SG-2-3-BCP@ have records that don't match to proper family | In prgoress, Spots FAMC problems but bugging on a FAMS one
AT 11 | US11
AT 12 | US12
AT 13 | US13

## Burndown
Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
2015-02-17 | 30 |  | 0
2015-03-03 | 24 | 6 | 53 | 60 | 53
2015-03-24 | 18 | 6 | 180 | 255 | 29.8824
2015-04-07 | 18 | 0 | 0 | 0 | #DIV/0!
2015-04-21 | 18 | 0 | 0 | 0 | #DIV/0!
2015-05-05 | 18 | 0 | 0 | 0 | #DIV/0!

## Sprint1
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US01 | Death before birth | AT01, AT02 | hm | Done | 150 | 60 | 120 | 90 | 2014-09-24
US02 | Death before birth | AT03 | LZ | DONE | 100 | 60 | 70 | 70
US03 | gender is wrong | AT04 | LZ | DONE | 100 | 60 | 60 | 30
US04 | More Than 15 Kids | AT04 | sg | Done | 20 | 20 | 22 | 30 | 40604
US05 | Two Identical Indvidauls | AT05 | sg | Done | 20 | 15 | 22 | 20
Review Results
Keep doing:
Meet twice a week
Text everyone when you discover a problem
Avoid:
Forgetting to commit changes to GitHub

## Sprint2
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US06 | nothing can happen after death date | AT06 | lz | done | 30 | 35 | 35 | 50 | 0.13043
US07 | divorce date cant be before married date | AT07 | lz | done | 30 | 40 | 50 | 75
US08 | Loop exists | AT08 | sg | done | 50 | 60 | 75 | 120
US09 | Individual is both a spouse and a parent | AT09 | sg | done | 15 | 12 | 20 | 10

## Sprint3
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed

## Sprint4
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed

## Sprint5
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed