## Team
Initials | First | Last | Email | GitHub Username
hc | Himabindu | Chaturvedula | hchaturv@stevens.edu | binduchaturvedula
sg | Stanislav | Grozny | sgrozny@stevens.edu | sgrozny
lg | Le | Zhanz | lzhang40@stevens.edu | zhangle2015
|  |  | GitHub Repository: | CS555_GEDCOM

## Backlog
Sprint | Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed | Added
1 | US01 | Death before birth | AT1 | lz | done | 25 | 30 | 25 | 20 | 2015-03-03
1 | US02 | Gender on parent is wrong | AT2 | lz | done | 20 | 25 | 20 | 20 | 2015-03-03
1 | US03 | Missing birth date | AT3 | hc | Done | 25 | 30 | 25 | 30 | 2015-03-03
1 | US04 | More than 15 kids | AT4 | sg | Done | 20 | 20 | 22 | 30 | 2015-03-03
1 | US05 | Two Identical Indviduals | AT5 | sg | Done | 15 | 15 | 22 | 20 | 2015-03-03
2 | US06 | nothing can happen after death date | AT6 | lz | done | 25 | 20 | 25 | 20 | 2015-03-24
2 | US07 | divorce date cant be before married date | AT7 | lz | done | 30 | 30 | 30 | 30 | 2015-03-24
2 | US08 | Loop exists | AT8 | sg | done | 50 | 60 | 130 | 120 | 2015-03-17
2 | US09 | Individual is both a spouse and a parent | AT9 | sg | done | 15 | 12 | 20 | 10 | 2015-03-23
3 | US10 | Individual records should match family recored | AT10 | sg | done | 50 | 60 | 90 | 90 | 2015-04-07
2 | US11 | Two Identical Children in a family | AT11 | hc | done | 15 | 30 | 15 | 50 | 2015-03-24
2 | US12 | No marriage date in a family | AT12 | hc | done | 15 | 30 | 25 | 60 | 2015-03-24
3 | US13 | Moms give birth | AT13 | hc | Done | 25 | 100 | 38 | 80 | 2015-04-07
3 | US14 | Parents are older | AT14 | hc | Done | 30 | 20 | 38 | 20 | 2015-04-07
4 | US15 | Be Alive First | AT15 | hc | Done | 50 | 40 | 36 | 60 | 2014-04-21
4 | US16 | Not always 9 months | AT16 | hc | Done | 100 | 120
| US17 | Dual Marriage | AT17
3 | US18 | Mom is under 5 years old | AT18 | lz | done | 25 | 30 | 30 | 40 | 2015-04-18
| US19 | Sibling Incest | AT19
4 | US20 | Legal Marriage | AT20 | lz |  | 100 | 120
4 | US21 | Polygamy | AT21 | sg | done | 100 | 60 | 130 | 60 | 2015-04-21
3 | US22 | Age is over 130 | AT22 | lz | In Progress | 25 | 30 | 30 | 40
| US23 | Only 1 set of parents or is it | AT23
4 | US24 | We aren't seahorses | AT24 | lz |  | 60 | 60
4 | US25 | NJ Pre 2013 | AT25 | sg |  | 50 | 30 | 50
| US26 | Third is more legal | AT26
| US27 | Teddy's Home | AT27
3 | US28 | Family Records should match individaul records | AT28 | sg | done | 150 | 60 | 200 | 90 | 2015-04-07

## Stories
Story ID | Story Name | Story Description | Acc Tests | Est Size | Est Time
US01 | Gender on parent | Make sure the gender on parent is correct | AT01 | 25 | 30
US02 | Death before marriage | Make sure the Marriage date is before death | AT02 | 20 | 25
US03 | Missing birth date | Make sure each and every individual with birth date | AT03 | 25 | 30
US04 | More than 15 kids | Make sure a family contains less than 15 kids | AT04 | 20 | 20
US05 | Two Identical Indvidauls | Make sure two people with the same name and birthdate don't appear | AT05 | 15 | 15
US06 | about death problem | nothing can happen after death date | AT06 | 25 | 20
US07 | about divorce date problem | divorce date cant be before married date | AT07 | 30 | 30
US08 | Loop exists | An individual is an ancestral child of self, | AT08 | 50 | 60
US09 | Individual is both a spouse and a parent | Check to see that an individual isn’t both a spouse and a child | AT09 | 15 | 12
US10 | Individual records don't match family recored | Make sure all info for individuals matches family records | AT10 | 50 | 60
US11 | Two Identical Children in a family | Two children can't share a name and birthdate | AT11 | 15 | 30
US12 | No marriage date in a family | Marriage date in a family doesn't exist | AT12 | 15 | 30
US13 | Moms give birth | BirthDate of children can't be after deathdate of mother | AT13 | 25 | 100
US14 | Parents are older | Birthdate of children can't be before birthdate of parents | AT14 | 30 | 20
US15 | Be Alive First | Deathdate of indvidual can't be before birthdate | AT15 | 50 | 40
US16 | Not always 9 months | Birthdate of Childrenin reasonable parameters with same mother , 90 -145 days are the apprixamte records for longest twin gap and earliest birth | AT16 | 100 | 120
US17 | Dual Marriage | Error if: Two marraiage events without a divorce or death occurance | AT17
US18 | Mom is under 5 years old | Mom is under 5 years old (record) | AT18 | 25 | 30
US19 | Sibling Incest | Siblings can't be married if biological siblings | AT19
US20 | Legal Marriage | All spouses have to be over 18 | AT20 | 100 | 120
US21 | Polygamy | Individual is a spouse to multipile families without a Divore or Deathdate | AT21 | 100 | 60
US22 | Age is over 130 | Age is over 130 | AT22 | 25 | 30
US23 | Only 1 set of parents or is it | An individual can't be a child to two families, unless a remarriage occured | AT23
US24 | We aren't seahorses | Only husband but no wife | AT24 | 60 | 60
US25 | NJ Pre 2013 | A family can't have more than 1 of each spouses | AT25 | 50 | 30
US26 | Third is more legal | first cousins should not marry one another | AT26
US27 | Teddy's Home | aunts and uncles should not marry their nephews or nieces | AT27
US28 | Family Records should match individaul records | Family Records should match individaul records | AT28 | 150 | 60
AT29

## Tests
AT ID | Story ID | Story Name | Input | Expected Output | Status
AT 01 | US01 | Death before birth | GED file, Individual Id,Bdays,Ddays | judge whether death before birth | done
AT 02 | US02
AT 03 | US03 | Missing birthdate | GED file, Individual Id,Bdays | All individuals with birthdates | Done
AT 04 | US04 | More than 15 Kids | GED File, Fam ID @F6@ has 16 kids. | Only Fam ID @F6@ is alerted and lists all childrens names | Done/Worked/Passed
AT 05 | US05 | Two Idenitcal Indviduals | Copied the information from indvidual 2 and 12 into indvidual 16 and 17 | Alerts to each set of copied indviduals and prints their information | Done/Worked/Passed
AT 06 | US06 | nothing can happen after death date
AT 07 | US07 | divorce date cant be before married date
AT 08 | US08 | Loop exists | GED File, Where an individaul is a child of its children | Alert if any node(individual) is revisited. So Individual A is looped, so it will alert on A, B, and D because B and D's children are A | Done
AT 09 | US09 | Individual is both a spouse and a parent | GED File, FAMS and FAMC match on an indvidual | Individual @SG-2-3-BCP@ will be spotted | Done
AT 10 | US10 | Individual records don't match family record | GED File, a FAMS or FAMC call to a family where that family doesn't have a matching tag | Individuals that have records that don't match to proper family. Will include: Individual record exists but family equivalent is null, Individual record exists but family record doesn't match, individual record exists but family to which it points doesn't | Done
AT 11 | US11 | Missing Marriage date for Family | GED file, family structure and total number of families | All families should have maggiage date | Done
AT 12 | US12 | checking for Same name and birth date for family | GED file, Family and Individual Structures | No children in family should have sama name and birth date | Done
AT 13 | US13 | mom gives birth | GED file, family structure and individual structure. | Mom with death date before birth date of kid@HC-3-1-F1@ | Done/Worked/Passed
AT 14 | US14 | Parents are older | GED file, family structure and individual structure. | Mom with birth date later birth date of kid@HC-3-1-F3@ | Done/Worked/Passed
AT18 | US18 | Mom is under 5 years old | GEDCOM file checks every wifes birtday vs all of her kids if the agedifference is 5 years or less it’s a problem | Return all mothers whose age was 5 or less at birthtime(regardless of current age) | In progress
AT22 | US22 | Age is over 130 | GED file, family structure and individual structure. | All individuals who are over 130 from todays date | In progress
AT 28 | US28 | Family Records should match individaul records | GED file, Family and Individual Structures | Families that have records that don't match to proper individual records. Will include: WIFE or HUSB tags point to individuals whose Spouse tag doesn't match family id, or Spouse tag is null, or individual doesn't exsist | Done
AT21 | US21 | Polygamy | GED file, Family and Individual Structures | If any individual is a spouse in several families an error might occur. For every non currnet family( family that isn't mrked as FAMS in individual record), if there is no divorce date for the family or a death date for the other spouse an error will occur. In addition, | Done
AT20 | US20 | NJPRE2013 | GED file, Family and Individual Structures | If any family has 2 HUSB or WIFE tags then it should alert when file is being parsed | Done
AT 15 | US15 | Be Alive First | GED file,Individual Structure | Date of birth comes first when compared to date of Death | Done
AT 16 | US16 | Not always 9 months | GED file, Family and Individual Structures | Difference between each children’s date of birth should be 90 to 145 days | Done

## Burndown
Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
2015-02-17 | 28 |  | 0
2015-03-03 | 24 | 4 | 53 | 60 | 53
2015-03-24 | 20 | 4 | 215 | 365 | 26.6301
2015-04-07 | 13 | 7 | 433 | 300 | 43.6
2015-04-21 | 5 | 8 | 300 | 240 | -33.25
2015-05-05 |  | 5 | 0 | 0 | #DIV/0!

## Sprint1
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US01 | Death before birth | AT01, AT02 | hm | Done | 150 | 60 | 120 | 90 | 2014-09-24
US02 | Death before birth | AT03 | LZ | DONE | 100 | 60 | 70 | 70
US03 | gender is wrong | AT04 | LZ | DONE | 100 | 60 | 60 | 30
US04 | More Than 15 Kids | AT04 | sg | Done | 20 | 20 | 22 | 30 | 40604
US05 | Two Identical Indvidauls | AT05 | sg | Done | 20 | 15 | 22 | 20
Review Results
Keep doing:
Meet twice a week
Text everyone when you discover a problem
Avoid:
Forgetting to commit changes to GitHub

## Sprint2
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US06 | nothing can happen after death date | AT06 | lz | done | 30 | 35 | 35 | 50 | 0.13043
US07 | divorce date cant be before married date | AT07 | lz | done | 30 | 40 | 50 | 75
US08 | Loop exists | AT08 | sg | done | 50 | 60 | 75 | 120
US09 | Individual is both a spouse and a parent | AT09 | sg | done | 15 | 12 | 20 | 10
US11 | Missing Marriage date | AT11 | hc | done | 15 | 30 | 15 | 50
US12 | Two identical children in family | AT12 | hc | done | 15 | 40 | 20 | 60

## Sprint3
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US10 | Individual records should match family recored | AT10 | sg | done | 50 | 60 | 90 | 90 | 2015-04-07
US28 | Family Records should match individaul records | AT28 | sg | done | 150 | 60 | 200 | 90 | 2015-04-07
US13 | Mom gives birth | AT 13 | hc | done | 30 | 100 | 43 | 120 | 2015-04-07
US14 | parents are older | AT 14 | hc | done | 60 | 20 | 40 | 10 | 2015-04-07
US18 | Mom is under 5 years old | AT 18 | lz | In progress | 25 | 30 | 30 | 40
US22 | Age is over 130 | AT 22 | lz | In progress | 25 | 30 | 30 | 40
Review Results
Most productive sprint
Keep doing:
Meet twice a week
Set weekly deadlines
Avoid:
Not communicating more when a problem appears

## Sprint4
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed | Comment | Comment at end
US24 | We aren't seahorses | AT24 | lz |  | 50 | 30 |  |  | 2014-04-21
US25 | NJ Pre 2013 | AT25 | sg |  | 60 | 60 | 50 | 20 | 2014-04-21 | Will probably take much longer as arcitecture will have to be modified | Ran error checking at start didn't have to reconstruct architecture
US16 | Not always 9 months | AT16 | hc | done | 100 | 120 | 50 | 60 | 2014-04-21
US20 | Legal marriage | AT19 | lz |  | 100 | 120 |  |  | 2014-04-21
US15 | Be Alive First | AT15 | hc | done | 50 | 40 | 40 | 60 | 2014-04-21
US18 | Mom is under 5 years old | AT18 | lz | In Progress | 25 | 30 | 30 | 40 | 2014-04-21 | Needs to finish
US21 | Polygamy | AT21 | sg | done | 100 | 60 | 130 | 60 | 2015-04-21
Review Results
Keep doing:
Avoid:

## Sprint5
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed