## Team
Initials | First | Last | Email | GitHub Username
hc | Himabindu | Chaturvedula | hchaturv@stevens.edu | binduchaturvedula
sg | Stanislav | Grozny | sgrozny@stevens.edu | sgrozny
lz | Le | Zhang | lzhang40@stevens.edu | zhangle2015
|  |  | GitHub Repository: | CS555_GEDCOM

## Backlog
Sprint | Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed | Added
1 | US01 | gender on parents |  | lz | Done | 15 | 40 | 23 | 30 | 2015-03-03
1 | US02 | Death before marriage |  | lz | Done | 20 | 50 | 27 | 61 | 2015-03-03
1 | US03 | Missing birth date |  | hc | Done | 25 | 30 | 25 | 30 | 2015-03-03
1 | US04 | More than 15 kids |  | sg | Done | 20 | 20 | 22 | 30 | 2015-03-03
1 | US05 | Two Identical Indviduals |  | sg | Done | 15 | 15 | 22 | 20 | 2015-03-03
US06
US07
US08
US09

## Stories
Story ID | Story Name | Story Description | Acc Tests | Est Size | Est Time
US01 | Gender on parents | Make sure the gender on parent is correct | AT01 | 15 | 40
US02 | Death before marriage | Make sure the Marriage date is before death | AT02 | 20 | 50
US03 | Missing birth date | Make sure each and every individual with birth date | AT03 | 30 | 30
US04 | More than 15 kids | Make sure a family contains less than 15 kids | AT04 | 20 | 20
US05 | Two Identical Indvidauls | Make sure two people with the same name and birthdate don't appear | AT05 | 20 | 15
US06
US07

## Tests
AT ID | Story ID | Story Name | Input | Expected Output | Status
AT 01 | US01 | Gender on parents | GED file,Individual name, gender | output whether anyone have a wrong gender | Done
AT 02 | US02 | Death before marriage | GED file, Individual deaddate,family marrieddate | output whether anyone have a wedding date after the date of his death | Done
AT 03 | US03 | Missing birthdate | GED file, Individual Id,Bdays | All individuals with birthdates | Done
AT 04 | US04 | More than 15 Kids | GED File, Fam ID @F6@ has 16 kids. | Only Fam ID @F6@ is alerted and lists all childrens names | Done/Worked/Passed
AT 05 | US05 | Two Idenitcal Indviduals | Copied the information from indvidual 2 and 12 into indvidual 16 and 17 | Alerts to each set of copied indviduals and prints their information | Done/Worked/Passed
AT 06 | US06
AT 07 | US07
AT 08 | US08
AT 09 | US09

## Burndown
Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
2015-02-17 | 30 |  | 0
2015-03-03 | 24 | 6 | 53 | 40 | 79.5
2015-03-24 | 24 | 0 | 0 | 0 | #DIV/0!
2015-04-07 | 24 | 0 | 0 | 0 | #DIV/0!
2015-04-21 | 24 | 0 | 0 | 0 | #DIV/0!
2015-05-05 | 24 | 0 | 0 | 0 | #DIV/0!

## Sprint1
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US01 | gender on parents | AT01 | lz | Done | 15 | 49 | 23 | 30 | 2015-03-03
US02 | Death before marriage | AT02 | lz | Done | 20 | 60 | 27 | 61 | 40604
US03
US04 | More Than 15 Kids | AT04 | sg | Done | 20 | 20 | 22 | 30 | 40604
US05 | Two Identical Indvidauls | AT05 | sg | Done | 20 | 15 | 22 | 20
Review Results
Keep doing:
Meet twice a week
Text everyone when you discover a problem
Avoid:
Forgetting to commit changes to GitHub

## Sprint2
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed

## Sprint3
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed

## Sprint4
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed

## Sprint5
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed